## Gantt Chart
Phase | Task Description | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Phase 1 | Data Acquisition & Exploration | bar: Week 1 to Week 2
Phase 2 | Data Preparation (Cleaning, Normalization) | bar: Week 2 to Week 3
Phase 3 | Dataset Construction & Feature Engineering | bar: Week 3 to Week 4
Phase 4 | Sequence Construction | bar: Week 4 to Week 5
Phase 5 | Model Development (LSTM Setup) | bar: Week 5 to Week 6
Phase 6 | Training & Initial Evaluation | bar: Week 6 to Week 7
Phase 7 | Iterative Improvements (Sequences + Tuning) | bar: Week 7 to Week 8
Phase 8 | Extended Experiment (MODIS 25 Years) | bar: Week 8 to Week 9
Phase 9 | Final Analysis & Report Writing | bar: Week 9